TECHNICAL & FINANCIAL PROPOSAL

Enterprise IT Infrastructure & Management System (EIMS)

Punjab Revenue Authority (PRA) | PITB

Submitted by: TechVista Systems (Pvt.) Ltd.

Bid Reference: PITB/PRA/EIMS/2025-26/001  |  Submission Date: 01 August 2025

# 1. Project Summary Dashboard

The table below provides a consolidated overview of all key parameters for this procurement engagement.

| PROJECT SUMMARY DASHBOARD |  |
| --- | --- |
| Project Name | PITB/PRA Enterprise IT Infrastructure & Management System |
| Client | Punjab Revenue Authority (PRA), Government of Punjab |
| Procurement Authority | Punjab Information Technology Board (PITB) |
| RFP Reference No. | PITB/PRA/EIMS/2025-26/001 |
| Project Value (PKR) | 612,500,000 (incl. O&M) |
| Contract Duration | 9 months (implementation) + 5 years (O&M) |
| Submission Deadline | 04 August 2025 – 3:00 PM (PST) |
| Procurement Method | QCBS – Quality and Cost Based Selection (70:30) |
| Minimum Technical Score | 70% (49 out of 70 marks) |
| Performance Security | 10% of total contract value |

All references to PPRA Rules are to the Punjab Procurement Rules 2014 as amended by Notification No. SO(IT)2-1/2021 dated 15 March 2021.

# 2. Pre-qualification & Eligibility Compliance

TechVista Systems satisfies all mandatory pre-qualification criteria as set out in Section 3 of the RFP. The compliance matrix below maps each criterion against our documented evidence.

| # | Criterion | Minimum Requirement | TechVista (Pvt.) Ltd. | Status |
| --- | --- | --- | --- | --- |
| 1 | Legal Registration | SECP reg., 7+ years operating | Incorporated 2013 (12 years) | PASS |
| 2 | Annual Turnover | Avg PKR 500M/year (last 3 FY) | PKR 563.7M avg (FY23-25) | PASS |
| 3 | Relevant Projects | 3 x Govt projects ≥ PKR 200M | 4 qualifying projects | PASS |
| 4 | Technical Staff | 50 FT staff; 5 CCIE/CCNP; 3 VCP; 2 CISSP | 163 FT; 7 CCIE/CCNP; 5 VCP; 3 CISSP | PASS |
| 5 | OEM Partnerships | 2 Gold OEM partnerships | 4 Gold (Cisco, HPE, Fortinet, VMware) | PASS |
| 6 | ISO 9001:2015 | Valid certificate required | Certified – expires Oct 2026 | PASS |
| 7 | ISO 27001:2022 | Valid certificate required | Certified – expires Mar 2027 | PASS |
| 8 | Tax Compliance | Active taxpayer, no blacklisting | Active ATL; no adverse record | PASS |

Supporting documents for all criteria above are provided in Annexures A through G of this proposal.

# 3. Bill of Quantities (Financial Proposal)

The itemized Bill of Quantities below covers all four components of the scope of work. All prices are firm, fixed, and inclusive of applicable taxes. Prices remain valid for 120 days from the submission date.

| # | Description | Qty | Unit Price (PKR) | Total (PKR) |
| --- | --- | --- | --- | --- |
| A | COMPONENT A – HARDWARE INFRASTRUCTURE |  |  | 267,900,000 |
| A.1 | Cisco UCS C240 M7 Rack Server | 22 | 5,200,000 | 114,400,000 |
| A.2 | HPE Primera 630 SAN Storage Array (600TB raw) | 2 | 28,500,000 | 57,000,000 |
| A.3 | Cisco Nexus 9504 Core Switch (pair) | 2 | 12,800,000 | 25,600,000 |
| A.4 | Fortinet FortiGate 3300E NGFW (HA pair) | 1 | 18,500,000 | 18,500,000 |
| A.5 | Structured Cabling Cat6A + Patch Panels | 1 lot | 8,200,000 | 8,200,000 |
| A.6 | Eaton 9395P 600kVA UPS + Battery Banks | 2 | 14,500,000 | 29,000,000 |
| A.7 | Precision Air Conditioning (N+1 config) | 4 | 3,800,000 | 15,200,000 |
| B | COMPONENT B – SOFTWARE & LICENSING |  |  | 121,600,000 |
| B.1 | VMware vSphere 8 Enterprise+ (22-host cluster) | 22 | 1,850,000 | 40,700,000 |
| B.2 | ServiceNow ITSM Platform (5-year subscription) | 1 | 32,000,000 | 32,000,000 |
| B.3 | Splunk Enterprise Security (5-year license) | 1 | 28,500,000 | 28,500,000 |
| B.4 | Microsoft Active Directory + Entra ID MFA | 1 | 12,000,000 | 12,000,000 |
| B.5 | Veeam Backup & Replication Enterprise Plus | 1 | 8,400,000 | 8,400,000 |
| C | COMPONENT C – IMPLEMENTATION SERVICES |  |  | 51,500,000 |
| C.1 | Professional Services – Design, Deploy, Integrate | 1 lot | 45,000,000 | 45,000,000 |
| C.2 | Training Program (50 PRA staff, 5 days) | 1 lot | 4,500,000 | 4,500,000 |
| C.3 | Documentation and Knowledge Transfer | 1 lot | 2,000,000 | 2,000,000 |
| D | COMPONENT D – O&M SERVICES (5 YEARS) |  |  | 140,000,000 |
| D.1 | Year 1 Annual O&M (24x7 NOC + Helpdesk) | 1 yr | 25,000,000 | 25,000,000 |
| D.2 | Year 2 Annual O&M | 1 yr | 26,500,000 | 26,500,000 |
| D.3 | Year 3 Annual O&M | 1 yr | 28,000,000 | 28,000,000 |
| D.4 | Year 4 Annual O&M | 1 yr | 29,500,000 | 29,500,000 |
| D.5 | Year 5 Annual O&M | 1 yr | 31,000,000 | 31,000,000 |
|  | TOTAL (Excl. Tax) |  |  | 581,000,000 |
|  | GST / Sales Tax on Services @ 16% |  |  | 31,500,000 |
|  | GRAND TOTAL (PKR) |  |  | 612,500,000 |

Note: The above BOQ prices include delivery, installation, commissioning, one-year onsite warranty, and all applicable Federal and Provincial taxes. Bid Security of PKR 5,000,000 (Pay Order) is enclosed separately.

# 4. Proposed Project Team

TechVista commits to deploying the following dedicated project team for the full project duration. All personnel listed are full-time employees of TechVista; no core roles will be subcontracted. CVs for all listed staff are attached in Annexure D.

| Name | Role | Qualifications | Experience | Allocation |
| --- | --- | --- | --- | --- |
| Mr. Usman Khalid | Project Manager / Bid Manager | PMP, CISM, MBA (IBA) | 15 yrs | 100% |
| Engr. Sara Mahmood | Lead Solutions Architect | CCIE (RS & SP), VCP-DCV 8 | 12 yrs | 100% |
| Mr. Bilal Chaudhry | Cybersecurity Engineer | CISSP, CEH, CCNP-Security | 10 yrs | 100% |
| Ms. Hira Nawaz | ITSM / ServiceNow Lead | ITIL v4 Master, CIS-ITSM | 8 yrs | 100% |
| Mr. Faisal Raza | Storage & Virtualization | VCP-DCV, VCP-NV, MCSE | 9 yrs | 100% |
| Mr. Adnan Malik | Senior Network Engineer | CCNP Enterprise, NSE-7 | 7 yrs | 100% |
| Ms. Zainab Javed | NOC Lead (O&M) | CCNA, ITIL v4 Foundation | 6 yrs | 100% (O&M) |
| Mr. Kashif Anwar | Database Administrator | Oracle OCA, MCDBA | 8 yrs | 50% |

## 4.1 Staff Certifications Summary

Total full-time technical staff: 80 engineers. Certifications held by the proposed team include:

- Cisco Certified Internetwork Expert (CCIE) – 2 engineers (Routing & Switching, Service Provider)

- Cisco Certified Network Professional (CCNP) – 5 engineers (Enterprise, Security, Data Center)

- VMware Certified Professional (VCP-DCV 8, VCP-NV) – 5 engineers

- Certified Information Systems Security Professional (CISSP) – 3 engineers

- ITIL v4 Master / Managing Professional – 4 engineers

- Project Management Professional (PMP) – 3 engineers

- Certified Information Security Manager (CISM) – 2 engineers

- ServiceNow Certified Implementation Specialist (CIS-ITSM) – 2 engineers

# 5. SLA Definitions & Incident Response Matrix

TechVista commits to the following Service Level Agreements (SLAs) for the O&M phase. SLA compliance will be tracked monthly in the ITSM platform and reported to PRA and PITB in quarterly SLA review meetings.

| Priority | Incident Type | Response Time | Resolution Time | Escalation | Penalty |
| --- | --- | --- | --- | --- | --- |
| P1 Critical | Complete service outage; data breach; core network failure | 15 min | 4 hours | CTO notified at 30 min | 0.5%/week LD |
| P2 High | Major functionality degraded; >50% users impacted | 30 min | 8 hours | PM notified at 2 hrs | 0.25%/week LD |
| P3 Medium | Partial service degradation; <50% users affected | 1 hour | 24 hours | Team Lead notified | Review in SLA report |
| P4 Low | Minor issues; cosmetic bugs; information requests | 4 hours | 72 hours | Standard queue | Tracked in CMDB |
| P5 Scheduled | Planned maintenance, firmware patches, upgrades | Scheduled | Per change plan | CAB approval required | None |

SLA penalties (Liquidated Damages) will be calculated on the quarterly O&M invoice value, subject to a maximum cap of 10% of the annual O&M contract value per year. SLA measurement will commence 30 days after Go-Live.

# 6. Implementation Milestones & Payment Schedule

The following payment milestones are proposed in alignment with the RFP's payment clause. Each milestone payment is conditional on formal written acceptance by PITB/PRA of the specified deliverables.

| # | Milestone | Target Date | Duration | Payment Trigger | Amount (PKR) |
| --- | --- | --- | --- | --- | --- |
| M0 | Contract Signing + Mobilization Advance | Sep 2025 | Week 1 | Upon contract execution | 61,250,000 |
| M1 | Site Readiness & Detailed Design Approved | Sep 2025 | Month 1 | Signed design approval | Included in M0 |
| M2 | Hardware Delivery & Rack Installation Complete | Dec 2025 | Months 2–4 | Factory Acceptance Test | 183,750,000 |
| M3 | Network Infrastructure Commissioned | Jan 2026 | Month 4 | Network acceptance sign-off | Included in M2 |
| M4 | Software Deployment & Integration Complete | Mar 2026 | Months 4–6 | Integration test report | 183,750,000 |
| M5 | UAT Sign-off + DR Drill Completed | May 2026 | Months 6–8 | UAT certificate from PRA | 122,500,000 |
| M6 | Go-Live + Training Completion + Handover | Jun 2026 | Month 9 | Go-Live certificate | 61,250,000 |
| M7–M11 | Annual O&M (Years 1–5) | Jul 2026+ | 5 years | Quarterly invoices | 140,000,000 |
|  | TOTAL |  |  |  | 612,500,000 |

## 6.1 Key Assumptions

- PRA will provide access to all three office floors and the server room within 2 weeks of contract signing.

- Existing generator capacity at PRA HQ is minimum 200kVA — TechVista will verify during site survey.

- All import duties and clearing charges for hardware are included in the quoted prices.

- Any change in scope beyond the agreed BOQ will be subject to a formal Change Request (CR) process with PITB approval.

- Force Majeure events will be excluded from SLA calculations in accordance with contract terms.

— End of Document —